**2017 Schedule**

SEPTEMBER

16th – We have a clear and fully developed understanding of the challenge.

16th to 23rd – We all (including the coaches) have indentified each 18 missions and we can explain to others what each missions is without any guidance or references.

23rd to 30th – Distribute programming to everyone… each person finds a way to solve their assigned mission and get a brief program for that mission.

30th to October 14st – Combine program(s) and add specific measurements

OCTOBER

14th to November 4th – Build Robot

NOVEMBER

4th to 11th- Solution

11th to 18th – Make Tri-fold board… somebody can take it home to finish

18th to December 2nd – Research on desalination experts and plants. Then we call them or meet them for expert review.

DECEMBER

2nd to 8th – We create and practice our performance. We should meet 3 times this week. The first day we can create our performance and then the last two days we can practice our performance.

\*This schedule is not an accurate schedule and can be changed depending our progress. This is just a baseline!! Also, we should plan to meet three times in the last three weeks before the competition so we can finish unfinished items.